April 16, 2015

Rachel Golson
Precision Drilling Corporation
800, 525-8th Avenue S.W.
Calgary, Alberta, Canada T2P 1G1

Rachel,

In reference to your Global HCM Master Data project, C CUBED Data Integrators would like to offer the following planning phase proposal and statement of work for you to consider.

Included in this phase are the following activities:

- Develop the project plan

- Review the project plan with key stakeholders

- Develop a detailed execution plan

- Develop a resource plan for execution

Once the development of the detailed execution plan and resource plan is underway, we will provide a proposal for the subsequent execution and delivery phases of the work.

Carla Cook						Bill Towsley

Managing Partner					Managing Partner 
SCHEDULE “A”

Statement of Work

| Client: | Precision Drilling Corporation |
| --- | --- |
| C CUBED DI Representatives: | Bill Towsley - Delivery Manager and SME Chris Marko – Project Manager |
| Start Date: | 2015-04-20 |
| End Date: | 2015-05-01 |

| Activity | Description | Primary | Add'l |
| --- | --- | --- | --- |
| Develop the project plan | Utilize ASAP methodology in conjunction with any Precision Drilling project management requirements to develop a project plan for the Global HCM Master Data project. Engage key Precision Drilling resources, as required, to ensure the resultant plan accurately reflects the requirement, timelines and constraints. | Chris Marko 20 hours | Bill Towsley 4 hours |
| Review the project plan with key stakeholders | Prior to developing a detailed execution plan, organize and facilitate a plan review with key stakeholders within IT, HR and the business. | Chris Marko 4 hours | Bill Towsley 2 hours |
| Develop a detailed execution plan | Working from the approved project plan, develop a detailed execution plan that is resource loaded. | Chris Marko 30 hours | Bill Towsley 2 hours |
| Develop a resource plan for execution | Utilizing the resource requirements from the detailed execution plan, develop a resource plan complete with the qualifications required to deliver activities within the detailed execution plan. | Chris Marko 26 hours | Bill Towsley 2 hours |

Rates:

| Chris Marko | Project Manager | $130/hr + GST |
| --- | --- | --- |
| Bill Towsley | MD SME | $155/hr + GST |
| Bill Towsley | Delivery Manager | Included |