## Resource plan
Phase 1
Activity | Primary | Add'l
Develop the charter | Chris Marko 20 hours | Bill Towsley 10 hours | 20 | 4
Develop the project plan | Chris Marko 17.5 hours | Bill Towsley 4 hours | 4 | 2
Develop a detailed execution plan | Chris Marko 19 hours | Bill Towsley 2 hours | 30 | 2
Develop a resource plan for execution | Chris Marko 18.5 hours | Bill Towsley 2 hours | 26 | 2
Phase 2
Activity | Primary | Add'l
Identify data object owner | Bill Towsley | Chris Marko
Document the current data requirements | Debabrata Rout | Bill Towsley Chris Marko
Review gaps | Debabrata Rout | Bill Towsley Chris Marko
Review HCM business processes | Bill Towsley | Debabrata Rout Chris Marko
Develop a data standard | Bill Towsley | Debabrata Rout Chris Marko
Develop any master data specific processes | Bill Towsley | Debabrata Rout Chris Marko
Identify gaps by profile existing data against the standard | Debabrata Rout | Pradeep Venneti Bill Towsley Chris Marko
Identify gaps in SAP configuration when compared to the standard | Debabrata Rout | Bill Towsley Chris Marko
Develop governance model | Bill Towsley | Chris Marko
Implement configuration changes | Debabrata Rout | Pradeep Venneti Chris Marko
Cleanse data | Debabrata Rout | Pradeep Venneti Bill Towsley Chris Marko
Implement data standard | Bill Towsley | Chris Marko
Implement governance | Bill Towsley | Chris Marko

## Expectations
Phase 1
Activity | C CUBED | Precision Drilling
Travel and expenses for site visits as required | Comply with Precision Drilling travel and expense policy | Provide Precision Drilling travel and expense policy guidance
Develop the project plan |  | Provide access to Global HCM Master Data project artifacts. Provide access to key business resources as required
Review the project plan with key stakeholders | Prepare plan synopsis/presentation | Identify key stakeholders and assist in making available
Develop a detailed execution plan |  | Identify Precision resources required by the plan activities
Develop a resource plan for execution
Phase 2
Activity | C CUBED | Precision Drilling
Travel and expenses for site visits as required | Comply with Precision Drilling travel and expense policy | Provide Precision Drilling travel and expense policy guidance
Identify data object owner |  | Provide access to Global HCM Master Data project artifacts. Provide access to key business resources as required
Document the current data requirements |  | Provide access to Global HCM Master Data project artifacts. Provide access to existing HCM processes, data "requirements" and reporting (as can be permitted) Provide access to key business resources
Review gaps
Review HCM business processes
Develop a data standard |  | Provide Precision resources required by the plan activities
Develop any master data specific processes
Identify gaps by profile existing data against the standard |  | Provide access to tools and technologies for data profiling/reporting. Consider requests for additional tools as recommended.
Identify gaps in SAP configuration when compared to the standard |  | Provide SAP access and/as necessary, resources.
Develop governance model |  | Provide access to key business resources as required
Implement configuration changes |  | Provide SAP access and/as necessary, resources.
Cleanse data |  | Provide access to tools and technologies for data cleansing Consider requests for additional tools as recommended.
Implement data standard |  | Provide access to key business resources as required
Implement governance

## Rates
Resource | Job | Billing Rate | GST | Travel/Exp* | Current Rate | 20% Reduction | Rate to Resource
Chris Marko | Project Manager | 130 | extra | included | 140 | 112 | 120
Bill Towsley | MD SME | 155 | extra | N/A | 175 | 140 | 145
Bill Towsley | Delivery Manager | included
Debabrata Rout | Functional Data analyst | 100 | extra | N/A | 110 | 88 | 90
Pradeep Venneti | Data analyst/developer | 110 | extra | N/A | 125 | 100 | 100
* travel, if required, to client locations outside Calgary not covered here