|  | HCM Processes, Master Data Cleanse and Governance |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Author: | Chris Marko, Bill Towsley | Program Sponsors: | Darren Ruhr |  |
|  | Date: | May 18, 2015 | Version: | 0.3 |  |

# Project Background

The overarching vision for Human Capital Management at Precision Drilling is to deliver operational excellence, with skilled staff delivering services through the application of common business policies and processes enabled by a consistent suite of systems.  Globally harmonized business processes call for a unified approach to management of our organizational and employee master data, taking into consideration localized business and regulatory requirements. The current business model is paperwork onerous and can result in handling delays impacting downstream systems and processes.  Inconsistencies of requirements and process by company and poor data quality controls cause manual re-work and negatively impact the quality of data for reporting.

Not included in the Global HCM Master Data project is any form of master data ownership, standards and governance that would ensure the revised processes deliver consistent content within the master data.  Without these additional components, there is a very real risk that, while the processes for requesting and creating are aligned across the enterprise, the data will not be able to support enterprise-wide management and reporting because of inconsistencies in the data content.

Ccubed Data Integrators will deliver the additional components efficiently and cost-effectively in conjunction with the Global HCM Master Data project.

# Project Definition

## Project Objectives

The primary goal of the project is to address existing and newly identified issues, eliminate the barriers, and implement the required changes to optimize and automate master data management processes through the use of people, processes and data, while leveraging current technology investments.

Project Objectives

This project has the following objectives:

- Improve efficiency, accuracy, and timeliness master data capture and system entry across the end to end process, beyond the bounds of technology

- Ensure that the improved master data process continues to facilitate the accurate and timely production of time evaluations, payroll results and general ledger entries and supports the financial reporting requirements of each business unit

- Identify qualitative and quantitative goals to achieve operational excellence, with expected benefits and appropriate supporting metrics with baseline and target measures

The project will address the current business model from a holistic perspective, assessing:

- Process – Does the process meet business requirements and have the right balance of controls vs. efficiency?

- Data – What are the key master data elements?  By whom and how will these be maintained?

- Technology – Does the current technology support the business process?

- Strategy – What strategic elements are missing or can be improved to enhance the effectiveness of data management?

- Structure – Are there issues from an organizational perspective contributing to the pain points?

## Critical Success Factors

The following factors have been deemed important to the success of this project and must receive special and continuing attention:

User Involvement and Ownership

- Users must be dedicated to the project and own its inputs and outcomes with representative participants across the end to end process

- User adoption of each cycle/phase of the project is crucial.  Due to the integrated nature of the roadmap, lack of adoption of one rollout will compromise the achievable benefits and success of subsequent project rollouts and the overarching program

Executive Management and HR/Payroll Leadership Support

- As significant behavioral change is expected, in addition to system additions and enhancements, executive support is crucial to support this transformation

Willingness to Drive and Adopt Change

- The continuous improvement approach for this project will deliver not only the end result of data standardization but also improved business processes.  This is intended to be an ongoing activity transforming the way work is managed and issues are resolved.  It is important to have the commitment from the stakeholder and management teams that this will be a part of daily operations going forward and will not end with project closure

Team Communication, Delivery Management, and Change Management

- Parallel work streams must communicate and update each other regularly – including Business, Change Management, Training, and SAP Support enabled by strong executive leadership and sound project management

- A key to the change management success will be to establish a foundation (baseline) then track and communicate the benefits to the business and the stakeholders through the lifecycle of the broader Program vs. separately by project

## Assumptions

The enterprise master data governance and standards initiative will be approved

Master Data accuracy will be improved.

Master Data quality reporting will be improved.

Data quality has a higher priority over schedule and budget

## Project Scope

The intention is deliver a series of impactful improvements to HR master data management aligned with the broader HR roadmap.

The project will confirm to SAP best practices and SAP ASAP Methodology, considering each master data object (e.g. Position) separately:

- Identify data object owner

- Document the current data requirements

- Review gaps (reporting, process “pain points” inconsistencies)

- Review HCM business processes (new from HCM project and existing out-of-scope for HCM master data)

- Develop a data standard

  - Based upon HCM business processes

  - Focus on required and conditionally required fields first

  - Consider “use-cases” (significant regional requirements, per hire vs post-hire enrichment)

- Develop any master data specific processes (sub-process to the HCM Master Data Processes)

- Identify gaps by profile existing data against the standard

  - Use existing tools/reporting

  - Develop as sustainable for post go-live data quality management

- Indentify gaps in SAP configuration when compared to the standard

- Develop governance model

  - Owner accountabilities

  - Indentify configuration changes

- Implement configuration changes

- Cleanse data

- Implement data standards

- Implement governance

### Out of Scope:

- Cleansing of historical data to conform to new global standards (any records prior to current/active record)

- Changes to Management Reports and distribution

- Change Management Processes

- Valuation on resources involved in the process having the proper skill sets.

- End to end user training

## Project Constraints

| Name | Summary |
| --- | --- |
| ETL tools may not be available | Data Services is SAP best practice to extract, transform and load data over ABAP/SQL |
| Data Analysis tools may not be available | Data Steward is SAP best practice for data quality metrics |
| Project Management Methodology | SAP uses waterfall project management to deliver projects, will need to modify to deliverables to a cycle/phase approach, will identity activities to run in parallel. |

## Project Assumptions

Contractor resources will be available on and off site Monday thru Friday

Contractor resources will be onsite for cutovers and go-live.

Internal resources will be dedicated to the project.

## Approach and Deliverables

| Phase | Approach | Deliverables |
| --- | --- | --- |
| Phase 1 - Preparation | - Project Planning - Resource Scheduling - Project Templates - SME meetings | - Develop Charter (Mini) - Develop High Level Project Plan - Develop Detailed Executable Plan - Develop Resource Plan for Execution |
| Phase 2 – Blueprint | - Pain point resolution working sessions / teams - Business requirements validation - TO BE processes documented - Configuration and programming design changes prototyped & documented | - Identify Data Object Owners - AS IS Data Requirements - Review Gaps - Review HCM Business Process - Develop Data Standards - Develop Master Data Specific Processes - Identify gaps between profiling existing data against the standard - Identify gaps in SAP configuration against standards - Develop Governance Model |
| Phase 2 - Realization | - Implement process and system changes - Documented standard operating procedures | - Implement Configuration changes - Cleanse Data - Implement Data Standard - Implement Data Governance |
| Phase 2 – Go Live | - Deploy process improvements | - Cleanse Data in production - Hand over data quality management reporting/tools |
| Phase 2 - Warranty | - Measure and monitor process improvements metrics | - Warranty Log |

# Project Organization

## Project Governance

Project will be governed by the change request process, decision request process, monthly status reporting, risk log, issue log, weekly team meetings and executable project plan updates.

## Project Organizational Structure

## Stakeholders

The project stakeholders are the groups or individuals who have a vested interest in the project process or outcome. The purpose in identifying the stakeholders is to ensure that stakeholder expectations are understood and to establish appropriate communication with the stakeholders in order to manage those expectations.

| Group/Department | Key Contacts | Interest |
| --- | --- | --- |
| Personnel | Pat Wagner Lee-Ann Triffo | Forms, process, data, and reporting changes for Canadian field employees |
| Global HR | Shellie Stone Elena Flores – Field Manasi Pandya - Corporate | Employee process and data model changes impacting Global HR processes and HR reporting |
| Talent Management | Tonia Emery | Employee data model changes impacting Talent Management processes and HR reporting |
| HRIS | Paul Sudzina | Process owner for Employee and Organizational Master Data |
| Talent Acquisition | Aron Ferchuk | Forms, process, data, and reporting changes impacting organizational management (integrated with SF Recruiting) and Onboarding |
| Benefits | Jennifer Fox | Forms, process, data, and reporting changes impacting Benefits Management |
| Compensation | Jennifer Fox | Forms, process, data, and reporting changes impacting Compensation Management |
| Payroll | Karen Kerkhoff | Forms, process, data and reporting changes impacting downstream Time Capture and Payroll Processing |
| Personnel | Pat Wagner – CA Drilling Lee-Ann Triffo – CA PWS | Forms, process, data and reporting changes impacting Personnel Processes (Recruiting, Onboarding, Employer and Employee initiated lifecycle changes) |
| Facilities and Office Services | Roberta Curnew Michelle Mouly | Impacts of changes to the onboarding, off boarding, and corporate transfer processes |
| IT Enterprise Service Delivery | Janine Maynard Kalpna Gill Allan Slavens | Impacts of changes to the onboarding, off boarding, and corporate transfer processes |
| IT SAP Delivery | Cledwyn D’Silva Wilson Yung | Delivery of sustainable solutions that will be transitioned to IT SAP Delivery for ongoing operational support |
| IT Business Systems Integration – FI & OPS | FI – Chris James OPS – Robert Koss | Integration impacts with Finance & Operations; design decision and resourcing support cross streams; support engagement of business leadership within Finance and Operations |
| Finance Operations Business Systems | Christopher Ames | Alignment of organizational structure with financial data structures (i.e. cost centres) |

# Risk Management

| Risk | Probability | Severity | Management Plan |
| --- | --- | --- | --- |
| Budget | M | H | Continuous improvement approach enables scaling delivery based on available funding |
| Uncommitted/unavailable business resources leads to an inability to plan and execute | M | H | Steering Committee will communicate program priorities and identify strong business representation. Backups will be identified and informed for coverage. Proactive planning to balance workload of ongoing support activities and program deliverables. If the scope of SAP enhancements is larger than originally estimated additional consulting support will be required |
| Stakeholder Groups Not Engaged | H | H | Ensure primary stakeholders attend and participate in workshops/meetings. If stakeholder groups were missed, review work completed to ensure alignment. Escalation to the Steering Committee where required. |
| Scope Creep | H | H | Clearly defined business objectives, scope, and constraints must be identified to ensure we have a clear and consistent understanding of what ‘done’ looks like |
| Stakeholders do not agree on the design for the processes or tools | M | H | Ensure roles and responsibilities for the Steering Committee are understood. Establish process to manage issues where they are elevated i.e. Executive Sponsor makes final decision. |

# Budget and Plan

## Estimated Budget

| Phase 2 | Budgeted Effort (Person Days) | Total Cost | Budgeted Labor | Contingency (10%) | Licensing | Travel Expense |
| --- | --- | --- | --- | --- | --- | --- |
| Blueprint | 264 | $287,496.00 | $261,360.00 | $26,136.00 | 0 | 0 |
| Realization | 176 | $191,664.00 | $174,240.00 | $17,424.00 | 0 | 0 |
| Final Preparation | 116 | $126,324.00 | $114,840.00 | $11,484.00 | 0 | 0 |
| Go-Live | 20 | $21,780.00 | $19,800.00 | $1,980.00 | 0 | 0 |
| Warranty | 40 | $43,560.00 | $39,600.00 | $3,960.00 | 0 | 0 |
| TOTAL | 616 | $670,824.00 | $609,840.00 | $60,984.00 | $0 | $0 |

## High Level Project Milestone Plan

| Milestones | Target Date |
| --- | --- |
| Commence Phase 2 | June 1. 2015 |
| Complete draft of first objects standard | July 10, 2015 |
| Complete draft of second objects standard | August 7, 2015 |
| Complete draft of third objects standards | August 28, 2015 |
| Complete testing of cleansing and configuration changes | October 30, 2015 |
| Go Live | December 7, 2015 |
| Warranty | December 21, 2015 |

## High Level Project Roadmap

| Activity | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Q4 | Q1 | Q2 | Q3 | Q4 |
| Phase 1 |  |  |  |  |  |
| Preparation |  |  |  |  |  |
| Phase 2 |  |  |  |  |  |
| Blueprint |  |  |  |  |  |
| Realization |  |  |  |  |  |
| Final Preparation |  |  |  |  |  |
| Go-Live |  |  |  |  |  |
| Warranty |  |  |  |  |  |

# Approval

|  |  | Signature |  | Date |
| --- | --- | --- | --- | --- |
| Program Sponsor |  |  |  |  |
|  |  | Darren Ruhr Senior Vice President, Corporate Services |  |  |

| Project Approver |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Carey Ford Senior Vice President,Operations Finance |  |  |  |  |  |  |  |  |
| Program Approver |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Brad Lindemann Vice President, Human Resources |  |  |  |  |  |  |  |  |
| Program Approver |  |  |  |  |  |  |  |  |  |
|  |  |  | Bob Klay Vice President – Information Technology |  |  |  |  |  |  |  |  |