## High Level Project Milestone Plan

| Milestones | Target Date |
| --- | --- |
| Commence Phase 2 | 2015-06-01 |
| Sprint 1 – Termination Process and Contractor Process |  |
| Design: |  |
| To Be Business Process Documents | 2015-06-11 |
| Standard Documents | 2015-06-22 |
| Data Standard Implementation Documents | 2015-06-25 |
| Governance Model Documents | 2015-06-26 |
| Build |  |
| Implement Configuration changes in QA | 2015-07-06 |
| Data Cleanse in QA | 2015-07-15 |
| User Acceptance in QA | 2015-07-22 |
| Execute and Go Live |  |
| Cutover Plan | 2015-07-24 |
| Execute Cutover Plan | 2015-07-27 |
| Go-Live | 2015-07-27 |
| Warranty | 2015-08-11 |
| Sprint 2 – Corporate Transfers & Assignment Changes Process, Iterative updates for Termination Process and Contractor Process |  |
| Design: |  |
| To Be Business Process Documents | 2015-08-05 |
| Standard Documents | 2015-08-12 |
| Data Standard Implementation Documents | 2015-08-14 |
| Governance Model Documents | 2015-08-17 |
| Build |  |
| Implement Configuration changes in QA | 2015-08-21 |
| Data Cleanse in QA | 2015-08-21 |
| User Acceptance in QA | 2015-08-26 |
| Execute and Go Live |  |
| Cutover Plan | 2015-08-27 |
| Execute Cutover Plan | 2015-08-31 |
| Go-Live | 2015-08-31 |
| Warranty | 2015-09-15 |
| Sprint 3 Operational Leaves of Absences Process, Iterative updates for Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process |  |
| Design: |  |
| To Be Business Process Documents | 2015-09-09 |
| Standard Documents | 2015-09-16 |
| Data Standard Implementation Documents | 2015-09-18 |
| Governance Model Documents | 2015-09-21 |
| Build |  |
| Implement Configuration changes in QA | 2015-09-23 |
| Data Cleanse in QA | 2015-09-23 |
| User Acceptance in QA | 2015-09-24 |
| Execute and Go Live |  |
| Cutover Plan | 2015-09-25 |
| Execute Cutover Plan | 2015-09-28 |
| Go-Live | 2015-09-28 |
| Warranty | 2015-10-13 |
| Sprint 4 On boarding Process, Iterative updates for Operational Leaves of Absences Process, Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process |  |
| Design: |  |
| To Be Business Process Documents | 2015-10-06 |
| Standard Documents | 2015-10-14 |
| Data Standard Implementation Documents | 2015-10-16 |
| Governance Model Documents | 2015-10-19 |
| Build |  |
| Implement Configuration changes in QA | 2015-10-22 |
| Data Cleanse in QA | 2015-10-22 |
| User Acceptance in QA | 2015-10-23 |
| Execute and Go Live |  |
| Cutover Plan | 2015-10-25 |
| Execute Cutover Plan | 2015-10-26 |
| Go-Live | 2015-10-26 |
| Warranty | 2015-11-09 |
| Sprint 5 - Iterative updates for On boarding Process, Operational Leaves of Absences Process, Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process |  |
| Design: |  |
| To Be Business Process Documents | 2015-11-03 |
| Standard Documents | 2015-11-10 |
| Data Standard Implementation Documents | 2015-11-13 |
| Governance Model Documents | 2015-11-16 |
| Build |  |
| Implement Configuration changes in QA | 2015-11-19 |
| Data Cleanse in QA | 2015-11-20 |
| User Acceptance in QA | 2015-11-25 |
| Execute and Go Live |  |
| Cutover Plan | 2015-11-26 |
| Execute Cutover Plan | 2015-11-30 |
| Go-Live | 2015-11-30 |
| Warranty | 2015-11-30 |