
Project Charter Lite

HCM Processes, Master Data Cleanse and Governance

	

	
	HCM Processes, Master Data Cleanse and Governance
	

	
	
	

	
	Author:
	Chris Marko, Bill Towsley
	Program Sponsors:
	Darren Ruhr
	

	
	Date:
	May 26, 2015
	Version:
	1.0 Final Review
	

	Updates: 

· Release has moved from “Big Bang” approach to a multi-release approach by sprints
· Budget break down by sprints

· Other updates as discussed 2015-05-25 @ 2:00 p.m. MDT
· Final Review


1. Project Background

The overarching vision for Human Capital Management at Precision Drilling is to deliver operational excellence, with skilled staff delivering services through the application of common business policies and processes enabled by a consistent suite of systems.  Globally harmonized business processes call for a unified approach to management of our organizational and employee master data, taking into consideration localized business and regulatory requirements. The current business model is paperwork onerous and can result in handling delays impacting downstream systems and processes.  Inconsistencies of requirements and process by company and poor data quality controls cause manual re-work and negatively impact the quality of data for reporting.
Not included in the Global HCM Master Data project is any form of master data ownership, standards and governance that would ensure the revised processes deliver consistent content within the master data.  Without these additional components, there is a very real risk that, while the processes for requesting and creating are aligned across the enterprise, the data will not be able to support enterprise-wide management and reporting because of inconsistencies in the data content.

C CUBED Data Integrators will deliver the additional components efficiency and cost-effectiveness in conjunction with the Global HCM Master Data project.
2. Project Definition
2.1. Project Objectives

The primary goal of the project is to address existing and newly identified issues, eliminate the barriers, and implement the required changes to optimize and automate master data management processes through the use of people, processes and data, while leveraging current technology investments.
Project Objectives

This project has the following objectives:

· Improve completeness and consistency of HCM master data that is captured during the execution of key “pain point” processes.
· Identify owners for subset master data associated with the processes being revised by the Global HCM Master Data program.
· Establish a master data governance process for the master data objects associated with the processes being revised by the Global HCM Master Data program that includes a Data Quality Management component
· Build master data management processes including data governance rules and compliance checking in the data request/gathering process
· Cleanse/enrich data as required to support new/revised business processes

The as part of the Global HCM Master Data program, this project will also address:

· Master Data Process – Does the process meet business requirements and does it have the right balance of controls vs. efficiency?

· Data – What are the key master data elements?  By whom and how will these be maintained?

· Technology – Does the current technology support the master data process? 

2.2. Critical Success Factors
The following factors have been deemed important to the success of this project and must receive special and continuing attention:

User Involvement and Ownership

· Users must be dedicated to the project and own its inputs and outcomes with representative participants across the end to end process 
· User adoption of each cycle/phase of the project is crucial.  Due to the integrated nature of the roadmap, lack of adoption of one rollout will compromise the achievable benefits and success of subsequent project rollouts and the overarching HCM program.
Executive Management and HR/Payroll Leadership Support

· Master Data governance requires leadership support at all levels to ensure compliance to standards and ensure action/reaction to Data Quality Management reporting and KPIs.
Willingness to Drive and Adopt Change

· Master data management processes can seem onerous to those with knowledge of “their” data. There must be acceptance and willingness to change to a paradigm of governance and control in order for this to be successful.
Team Communication, Delivery Management, and Change Management

· As a project within the Global HCM Master Data program, the HCM Master Data Governance and Cleanse project must fully integrate with the activities of the rest of the program in order to avoid duplicated effort. This also means that the other initiatives within the program must e fully aware of activities taking place with this project.
2.3. Assumptions
· Training and change management for the HCM Master Data Governance and Cleanse project will be provided by the overarching Global HCM Master Data program.  The data team will have input into and QA the master data materials.
· Testing activities for the HCM Master Data Governance and Cleanse project will be provided by the overarching Global HCM Master Data program.
· Within the approved budget, the scope and/or schedule for data cleansing / enrichment / remediation activities will be adjusted in order to ensure data quality and compliance to standard.
2.4. Project Scope
The intention is deliver a series of improvements to HCM master data management aligned with the broader HR roadmap.
The scope of the project will include/address:
· Master data object ownership
· A master data governance model and process
· A living document master data standard for governed fields of master data objects associated with the processes being revised by the Global HCM Master Data program 
· Master data management processes (sub-process to the HCM Master Data Processes) including requests (data gathering/submission), workflow and approval
· A data quality management process and tools (sustainable for post go-live) to measure data quality against the standard
· Profile existing data against the standard (data assessment)
· Data cleansing/enrichment/remediation to support the processes being revised by the Global HCM Master Data program
2.4.1. Out of Scope:

· Cleansing of historical data to conform to new global standards (any records prior to current/active record)
· Changes to Management Reports and distribution
· Valuation on resources involved in the process having the proper skill sets.

2.5. Project Constraints

	Name
	Summary

	ETL tools may not be available
	SAP Data Services is SAP best practice to extract, transform and load data over ABAP/SQL

	Data Analysis tools may not be available
	SAP Information Steward is SAP best practice for data quality metrics over ABAP/SQL /SPINIFEX

	Project Management Methodology
	SAP uses waterfall project management to deliver projects, have modified the deliverables using a release/cycle approach, and to identity activities that can run in parallel. 

	
	


2.6. Project Assumptions

· Contractor resources will be available on and off site Monday thru Friday

· Contractor resources will be onsite for cutovers and go-live.
· Internal resources will be dedicated to the project.
2.7. Approach and Deliverables 
	Approach
	Global HCM Master Data
	Data Team

	Phase 1
	
	

	Preparation
	· Review and approval
	· Develop Charter (Mini)

· Develop High Level Project Plan

· Develop Detailed Executable Plan

· Develop Resource Plan for Execution

	Phase 2
	
	

	Diagnosis/Discovery
(Prep)
	· Pain point resolution working sessions / teams(iterative)
	· Identify data objects (high level)

	Design

(Blueprint)
	· Business requirements validation

· High Level TO BE design
· Gap assessment
	· Data object scope

· High level data quality assessment

· Data object owners

· TO BE data standards

· TO BE master data processes (DQM and changes to request/gathering

· Governance model and owner accountability

	Build

(Realization)
	· Process documentation (PDD)
· Configuration (CCD)

· Development (except config)

· Business Process Procedures (BPP)
· Develop training material

· Create and execute test scripts
	· Formalize master data standards and master data process

· Process documentation (PDD)

· Configuration (CCD)

· DQM reporting
· Detailed cleansing specifications (DCDD)

· Create data content (missing/other sources)

· Business Process Procedures (BPP)
· QA training material

· Unit test cleansed data

	Deploy

(Final prep/Go Live)
	· Finalize and execute cutover plan
· Deliver training

· Implement procedures

· Warranty support
	· Data cleansing in prod


3. Project Organization
3.1. Project Governance
Project will be governed by the change request process, decision request process, monthly status reporting, risk log, issue log, weekly team meetings and executable project plan updates.
3.2. Project Organizational Structure
[image: image1.emf]HCM Program Executive 

Sponsor

Darren Ruhr

HCM Program Steering 

Committee

HCM Program Operating 

Committee

Karen Kerkhoff

PY Business Lead

Rachel Golson –HCM Business Systems Integration Lead

Vacant –HCM Project Manager (Rachel Golson Interim Backfill)

Paul Sudzina

HR Business Lead

Project Organizational Chart

Global HR Master Data

Janine Maynard

IT Service Enterprise 

Delivery

Roberta Curnew

Michelle Mouly

Facilities & Office 

Services

Sandra Carrasco

HRIS Business Analyst

Selest Haberstock

HR Business Analyst

Canada

Angie Clark

Business Process 

Improvement Lead

Shellie Stone

Global HR

Manasi Pandya

HR Corporate

Elena Flores

US HR Field

Tonia Emery

Talent & 

Development

Jennifer Fox

Total Rewards

Linda Flores

HRIS Supervisor

Mike Fields

HCM Solution Lead

Monica Despres

HCM Functional 

Analyst

Vacant

HCM Developer

Cledwyn D’Silva

IT SAP Systems 

Delivery

Wilson Yung

IT SAP Sys Del-

Development 

Jeanne Gillespie

IT SAP Security 

Analyst

Robert Koss

Business Systems 

Integration OPS

Pat Wagner

Lee-Ann Triffo

CA Personnel

Chris James

Business Systems 

Integration FIN

Christopher Ames

Finance Operations 

Business Systems

Debra Rusk

Global Payroll

Colette Minor

US Payroll

Rick Brummund

GEC Payroll

Crystal Jackson

CA Payroll

Basis Team

SAP Netweaver 

Analysts/DBAs

Core Team

Supporting Team

Legend

Vacant

HCM Training 

Specialist

Tina Callisto

HR Training Specialist

Vacant

HCM Functional 

Analyst (Employee)

Bill Towsley

HCM Data Quality & 

Integration

Manasi Pandya

HR Corporate

Darren Ruhr, Carey Ford, Brad 

Lindemann, Grant Hunter, Ross 

Pickering, Deric Simmons, Bob 

Klay, Rachel Golson

Tonia Emery, Aron Ferchuk, Roy McClung, Shellie 

Stone, Jennifer 

Fox, Paul Sudzina, Karen Kerkhoff, Rachel Golson, Deric 

Simmons, Pat Wagner, Lee-Ann Triffo


Stakeholders
The project stakeholders are the groups or individuals who have a vested interest in the project process or outcome. The purpose in identifying the stakeholders is to ensure that stakeholder expectations are understood and to establish appropriate communication with the stakeholders in order to manage those expectations.
	Group/Department
	Key Contacts
	Interest

	Global HR 
	Shellie Stone
Elena Flores – Field

Manasi Pandya - Corporate
	Employee process and data model changes impacting Global HR processes and HR reporting

	Talent Management
	Tonia Emery
	Employee data model changes impacting Talent Management processes and HR reporting

	HRIS
	Paul Sudzina
	Process owner for Employee and Organizational Master Data 

	IT SAP Delivery
	Cledwyn D’Silva
Wilson Yung
	Delivery of sustainable solutions that will be transitioned to IT SAP Delivery for ongoing operational support


4. Risk Management
	Risk
	Probability
	Severity
	Management Plan

	Budget


	M
	H

	Continuous improvement approach enables scaling delivery based on available funding 


	Additional Developer maybe required for Data Cleansing
	M
	H
	Depending cleansing scope definition and  analysis and additional resource may be required 

	SAP customization/non-standard configuration 
	H
	M
	Identify custom fields and tables early and adjust detailed execution plan to accommodate requirements.


5. Budget and Plan
5.1. Estimated Budget 
	Phase 2
	Budgeted Effort
(Person Days)
	Total Cost
	Budgeted

Labor
	Contingency (10%)
	Licensing
	Travel Expense

	Sprint 1
	76
	$68,227.50


	$62,025.00


	$6,202.50


	0
	0

	Sprint 2
	45
	$38,568.75


	$35,062.50


	$3,506.25


	0
	0

	Sprint 3
	47

	$40,177.50


	$36,525.00


	$3,652.50


	0
	0

	Sprint 4
	47

	$40,177.50


	$36,525.00


	$3,652.50


	0
	0

	Sprint 5
	67

	$57,213.75


	$52,012.50


	$5,201.25


	0
	0

	TOTAL
	282

	$244,365.00


	$222,150.00


	$22,215.00


	0
	0


5.2. High Level Project Milestone Plan
	Milestones
	Target Date

	Commence Phase 2
	2015-06-01

	Sprint 1 – Termination Process and Contractor Process
	

	Design: 
	

	To Be Business Process Documents
	2015-06-11

	Standard Documents
	2015-06-22

	Data Standard Implementation Documents 
	2015-06-25

	Governance Model Documents 
	2015-06-26

	Build
	

	Implement Configuration changes in QA
	2015-07-06 

	Data Cleanse in QA 
	2015-07-15 

	User Acceptance in QA
	2015-07-22 

	Execute and Go Live
	

	Cutover Plan
	2015-07-24 

	Execute Cutover Plan
	2015-07-27 

	Go-Live
	2015-07-27 

	Warranty
	2015-08-11 

	
	

	Sprint 2 – Corporate Transfers & Assignment Changes Process, Iterative updates for Termination Process and Contractor Process
	

	Design: 
	

	To Be Business Process Documents
	2015-08-05 

	Standard Documents
	2015-08-12

	Data Standard Implementation Documents 
	2015-08-14 

	Governance Model Documents 
	2015-08-17 

	Build
	

	Implement Configuration changes in QA
	2015-08-21

	Data Cleanse in QA 
	2015-08-21

	User Acceptance in QA
	2015-08-26

	Execute and Go Live
	

	Cutover Plan
	2015-08-27

	Execute Cutover Plan
	2015-08-31

	Go-Live
	2015-08-31

	Warranty
	2015-09-15

	
	

	Sprint 3 Operational Leaves of Absences Process, Iterative updates for Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process
	

	Design: 
	

	To Be Business Process Documents
	2015-09-09

	Standard Documents
	2015-09-16

	Data Standard Implementation Documents 
	2015-09-18

	Governance Model Documents 
	2015-09-21

	Build
	

	Implement Configuration changes in QA
	2015-09-23

	Data Cleanse in QA 
	2015-09-23

	User Acceptance in QA
	2015-09-24

	Execute and Go Live
	

	Cutover Plan
	2015-09-25

	Execute Cutover Plan
	2015-09-28

	Go-Live
	2015-09-28

	Warranty
	2015-10-13

	
	

	Sprint 4 On boarding Process, Iterative updates for Operational Leaves of Absences Process, Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process
	

	Design: 
	

	To Be Business Process Documents
	2015-10-06

	Standard Documents
	2015-10-14

	Data Standard Implementation Documents 
	2015-10-16

	Governance Model Documents 
	2015-10-19

	Build
	

	Implement Configuration changes in QA
	2015-10-22

	Data Cleanse in QA 
	2015-10-22

	User Acceptance in QA
	2015-10-23

	Execute and Go Live
	

	Cutover Plan
	2015-10-25

	Execute Cutover Plan
	2015-10-26

	Go-Live
	2015-10-26

	Warranty
	2015-11-09 

	
	

	Sprint 5 - Iterative updates for On boarding Process, Operational Leaves of Absences Process, Corporate Transfers & Assignment Change Process, Termination Process and Contractor Process
	

	Design: 
	

	To Be Business Process Documents
	2015-11-03

	Standard Documents
	2015-11-10 

	Data Standard Implementation Documents 
	2015-11-13

	Governance Model Documents 
	2015-11-16

	Build
	

	Implement Configuration changes in QA
	2015-11-19

	Data Cleanse in QA 
	2015-11-20

	User Acceptance in QA
	2015-11-25

	Execute and Go Live
	

	Cutover Plan
	2015-11-26

	Execute Cutover Plan
	2015-11-30

	Go-Live
	2015-11-30

	Warranty
	2015-11-30


5.3. High Level Project Roadmap

	Activity
	2015
	2016

	
	Q1
	Q2
	Q3
	Q4
	Q1

	Phase 1
	
	
	
	
	

	Preparation
	
	
	
	
	

	Phase 2 
	
	
	
	
	

	Sprint 1
	
	
	
	
	

	Sprint 2
	
	
	
	
	

	Sprint 3
	
	
	
	
	

	Sprint 4
	
	
	
	
	

	Sprint 5
	
	
	
	
	

	
	
	
	
	
	


6. Approval

	
	
	Signature
	
	Date



	Program Sponsor
	
	
	
	

	
	
	Darren Ruhr

Senior Vice President, Corporate Services
	
	


	Project Approver
	
	
	
	

	
	
	Carey Ford

Senior Vice President,Operations Finance
	
	

	Program Approver
	
	
	
	

	
	
	Brad Lindemann

Vice President, Human Resources
	
	

	       Program Approver
	
	
	
	

	 
	
	Bob Klay

Vice President – Information Technology
	  
	


S:\Projects\Current\Global HCM Program\Projects\Global Master Data\Project Charter - Global HCM Master Data.docx
Page  1
Project Charter – HCM Processes, Master Data Cleanse and Governance
Page  2

