## Budget
|  | 2015 | [5 empty] | 2016
Resources | June | July | August | September | October | November | December | January | Februaruy
Bill Towsley | 14 | 0 | 16 | 21 | 17 | 20 | 15 | 20 | 20
Chris Marko | 22 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 10
Pradeep Venneti | 0 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 20
Debabrata Rout | 22 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 10
Jennifer Lengsfeld | 0 | 18 | 20 | 21 | 21 | 20 | 15 | 20 | 10
HCM Business SME | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 5
Rachel Golson | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Cycle 1 Process SME | 15 | 15 | 15 | 15 | 10 | 3 | 0 | 0 | 0
Cycle 2 Process SME | 15 | 15 | 15 | 15 | 10 | 3 | 0 | 0 | 0
Cycle 3 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0
Cycle 4 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0
Cycle 5 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0

## Actuals and Forecast
| 2015 | [6 empty] | 2016
Resources | June | July | August | September | October | November | December | January | Februaruy
Bill Towsley | 14 | 0 | 16 | 21 | 17 | 20 | 15 | 20 | 20
Chris Marko | 22 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 10
Pradeep Venneti | 0 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 20
Debabrata Rout | 22 | 20 | 20 | 21 | 21 | 20 | 15 | 20 | 10
Jennifer Lengsfeld | 0 | 18 | 20 | 21 | 21 | 20 | 15 | 20 | 10
HCM Business SME | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 5
Rachel Golson | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Cycle 1 Process SME | 15 | 15 | 15 | 15 | 10 | 3 | 0 | 0 | 0
Cycle 2 Process SME | 15 | 15 | 15 | 15 | 10 | 3 | 0 | 0 | 0
Cycle 3 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0
Cycle 4 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0
Cycle 5 Process SME | 0 | 0 | 10 | 15 | 15 | 15 | 10 | 3 | 0

## Summary
| 2015 | [20 empty] | 2016
Resources | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | Februaruy |  |  | Totals
| Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance
Bill Towsley | 14 | 14 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 21 | 21 | 0 | 17 | 17 | 0 | 20 | 20 | 0 | 15 | 15 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 143 | 143 | 0
Chris Marko | 22 | 22 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 15 | 15 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 169 | 169 | 0
Pradeep Venneti | 0 | 0 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 15 | 15 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 157 | 157 | 0
Debabrata Rout | 22 | 22 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 15 | 15 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 169 | 169 | 0
Jennifer Lengsfeld | 0 | 0 | 0 | 18 | 18 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 15 | 15 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 145 | 145 | 0
HCM Business SME | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 5 | 5 | 0 | 115 | 115 | 0
Rachel Golson | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 45 | 45 | 0
Cycle 1 Process SME | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 0
Cycle 2 Process SME | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 0
Cycle 3 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 68 | 68 | 0
Cycle 4 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 68 | 68 | 0
Cycle 5 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 10 | 10 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 68 | 68 | 0