## Budget
|  | 2015 | [5 empty] | 2016
Resources | June | July | August | September | October | November | December | January | Februaruy
Bill Towsley - MD Lead SME and Delivery Manager | 14 | 0 | 16 | 21 | 17 | 20 | 10 | 0 | 0
Chris Marko - PM/MD Technical Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradeep Venneti - ABAP/SQL Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debabrata Rout - Functional/Technical BA | 22 | 20 | 20 | 21 | 21 | 20 | 10 | 0 | 0
Jennifer Lengsfeld - Functional BA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM Business SME | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 0 | 0
Rachel Golson | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
Termination Process SME | 15 | 15 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Contractor Process SME | 15 | 15 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Corporate Transfers & Assignment Changes Process SME | 0 | 0 | 15 | 5 | 5 | 5 | 0 | 0 | 0
Operational Leaves of Absences Process SME | 0 | 0 | 0 | 15 | 5 | 5 | 0 | 0 | 0
Onboarding Process SME | 0 | 0 | 0 | 0 | 15 | 5 | 0 | 0 | 0
Project Manager | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 0 | 0
DM Technical Lead | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 0 | 0
Basis | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Security | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Developer | 0 | 20 | 20 | 21 | 21 | 20 | 5 | 0 | 0

## Actuals and Forecast
| 2015 | [6 empty] | 2016
Resources | June | July | August | September | October | November | December | January | Februaruy
Bill Towsley - MD Lead SME and Delivery Manager | 14 | 0 | 16 | 21 | 17 | 20 | 10 | 0 | 0
Chris Marko - PM/MD Technical Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradeep Venneti - ABAP/SQL Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debabrata Rout - Functional/Technical BA | 22 | 20 | 20 | 21 | 21 | 20 | 10 | 0 | 0
Jennifer Lengsfeld - Functional BA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM Business SME | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 0 | 0
Rachel Golson | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
Cycle 1 Process SME | 15 | 15 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Cycle 2 Process SME | 15 | 15 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Cycle 3 Process SME | 0 | 0 | 15 | 5 | 5 | 5 | 0 | 0 | 0
Cycle 4 Process SME | 0 | 0 | 0 | 15 | 5 | 5 | 0 | 0 | 0
Cycle 5 Process SME | 0 | 0 | 0 | 0 | 15 | 5 | 0 | 0 | 0
Project Manager | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 0 | 0
DM Technical Lead | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 0 | 0
Basis | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Security | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Developer | 0 | 20 | 20 | 21 | 21 | 20 | 5 | 0 | 0

## Summary
| 2015 | [20 empty] | 2016
Resources | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | Februaruy |  |  | Totals
| Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance | Budget | Act/FC | Variance
Bill Towsley - MD Lead SME and Delivery Manager | 14 | 14 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 21 | 21 | 0 | 17 | 17 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 98 | 0
Chris Marko - PM/MD Technical Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradeep Venneti - ABAP/SQL Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debabrata Rout - Functional/Technical BA | 22 | 22 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 134 | 0
Jennifer Lengsfeld - Functional BA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM Business SME | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 95 | 0
Rachel Golson | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0
Cycle 1 Process SME | 15 | 15 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0
Cycle 2 Process SME | 15 | 15 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0
Cycle 3 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0
Cycle 4 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0
Cycle 5 Process SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0
Project Manager | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 15 | 15 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 95 | 0
DM Technical Lead | 20 | 20 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0
Basis | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0
Security | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0
Developer | 0 | 0 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 20 | 20 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 107 | 0